## V0.1 Buy List
Slipstream V0.1 — Bench Build Procurement
Window: Q3 2026 – Q1 2027 · Budget bucket $13,000–21,000 (Roadmap II.1) · prices = researched street, blue = update at PO
Phase | Track | Item | Spec / SKU | Vendor (researched) | Unit $ | Qty | Ext $ | Status | Notes / trigger
1 | SS01 | EVE LF280K V3 cell, Grade A | 3.2V 280Ah prismatic, QR-verified | GobelPower / Docan (US stock) / 18650BatteryStore | 66 | 16 | 1056 | To order | LONG LEAD — order first. Confirm side-lay orientation with distributor before PO (SS01 Q1)
1 | SS01 | JK BMS | PB2A16S20P 16S 200A, 2A active balance, CAN/RS485 | JKBMS / Docan kit | 250 | 1 | 250 | To order | CAN profile to Cerbo is SS01 Q4
1 | SS01 | Pack heater pad + thermostat | 48V silicone, BMS-interlocked | generic | 100 | 1 | 100 | To order | Charge lockout <0°C regardless
1 | SS01 | Class-T fuse + holder + disconnect + busbar | 200A class | Blue Sea / Victron | 250 | 1 | 250 | To order
1 | SS02 | Victron MultiPlus-II 48/3000/35 | inverter/charger | authorized Victron dealer | 1200 | 1 | 1200 | To order | Shared platform slug w/ House BUS
1 | SS02 | Victron SmartSolar MPPT 250/60-Tr | SCC125060221 | Off Grid Stores ~$435 / solar-electric ~$415 | 435 | 1 | 435 | To order
1 | SS02 | Victron Cerbo GX MK2 | system monitor + relays | Amazon / dealer | 300 | 1 | 300 | To order
1 | SS02 | Victron GX LTE 4G | cellular for VRM | dealer | 250 | 1 | 250 | To order | Buy — earns its keep at the campsite
1 | SS02 | Victron SmartShunt 500A | SoC truth independent of JK BMS | dealer | 130 | 1 | 130 | To order
1 | SS02 | Lynx Distributor (or equiv busbar/fusing) | MEGA branch fusing | dealer | 250 | 1 | 250 | To order
1 | SS02 | NEMA 14-50 inlet + outlet + adapter kit | 50→30→20→15A adapters | various | 350 | 1 | 350 | To order
1 | SS02 | DC-DC 48→24V 25A + 48→12V 30A | two rails, fused | Victron Orion-Tr / Mean Well | 300 | 1 | 300 | To order | 24V rail feeds actuators (SS03)
1 | SS02 | Smart relays/contactors | water heater + AC precondition | various | 120 | 1 | 120 | To order
1 | SS02 | Wiring, lugs, conduit, breakers | 6 AWG main runs + branch | various | 500 | 1 | 500 | To order
2 | SS03 | Progressive PA-17-24-2000 actuator | 24V, 24" stroke, 2,000 lb, IP65 | Progressive Automations | 380 | 4 | 1520 | To order | Confirm 24V coil + limit switch config at order
2 | SS03 | 4-ch sync controller + encoders | hall/encoder closed-loop | FIRGELLI FCB-4 / PA box / DIY ESP32 | 300 | 1 | 300 | To order | SS03 Q1 decides which; budget covers any
2 | SS03 | Test rig steel + 200 lb load + hardware | bench frame at true corner geometry | local steel yard | 250 | 1 | 250 | To order
2 | SS03 | Limit switches + manual override drill drive | stuck-up recovery | various | 100 | 1 | 100 | To order
2 | SS04 | XPS 1" sheets (Foamular 250) | stack A core, 2× 4x8 | big box | 30 | 2 | 60 | To order
2 | SS04 | PIR/PU board 1" | stack B core, 2× 4x8 | big box | 35 | 2 | 70 | To order
2 | SS04 | PET foam (Airex T92 class) sample | stack C core, 2'x4' | composites supplier | 120 | 1 | 120 | To order
2 | SS04 | E-glass roll + epoxy kit + consumables | 6 oz + biax, vacuum-bag film/tacky tape | US Composites / Fibre Glast | 450 | 1 | 450 | To order
3 | SS01 | Pack enclosure fabrication | Al sheet + compression fixture, IP67 target | frame fabricator or sheet-metal shop | 1200 | 1 | 1200 | To order | AFTER side-lay answer + SS05 rail section freeze
3 | SS06 | CFD compute (OpenFOAM cloud spot) | ~25M cell runs × matrix | AWS/GCP spot | 400 | 1 | 400 | To order | Self-run keeps swing item low
3 | SS06 | Methodology audit (consultant spot-check) | one run reviewed | freelance aero | 800 | 1 | 800 | To order | Optional but cheap insurance
3 | SS06 | 1:8 wind tunnel article + session | FDM print + fill/sand + tunnel day | university aero lab (quote) | 1300 | 1 | 1300 | To order | SS06 Q3: get 2 quotes
3 | — | Interior mockup materials | cardboard/foam 1:1 cabin | big box | 300 | 1 | 300 | To order | Gate 6 walkthrough
3 | — | Documentation + misc tooling | crimper, torque wrench, labels | various | 450 | 1 | 450 | To order
|  | Subtotal |  |  |  |  | 12811
|  | Contingency (15%) |  |  | 15% |  | 1921.65
|  | TOTAL |  |  |  |  | 14732.65
Roadmap bucket check (II.1)
|  | Bucket | Track | Roadmap range | This list
|  | Cells + BMS + enclosure | SS01 | 5,000–7,000 | 2856
|  | Inverter/MPPT/Cerbo/wiring | SS02 | 3,000–4,000 | 3835
|  | Actuators + sync + rig | SS03 | 2,000–3,000 | 2170
|  | Composite samples | SS04 | 500–1,000 | 700
|  | CFD + wind tunnel | SS06 | 2,000–5,000 | 2500
|  | Mockup/tooling/misc | — | 500–1,000 | 750
Order sequence: Phase 1 now (cells are the long-lead pole + electrical spine for Gate 2) → Phase 2 on cell-ship confirmation → Phase 3 after side-lay answer + geometry freeze.